## Sheet1
2020 - 2026 SWM CIP Update
Project No. | Project Name | Priority Score | Estimated Cost 2020-2026 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | Future Years
CIP Projects
40 | Stormwater Contribution to City of Federal Way Public Works Complex | 76 | 8000000 | 2026: 2000000 | 6000000
No outside funding assumed.
3 | Cold Creek Culvert Replacements and Channel Stabilization | 70 | 3800000 | 2020: 500000; 2021: 500000; 2022: 1000000; 2023: 1800000
| Assumption: Potential for funding for the construction component of this project to improve fish passage |  |  | 2023: -500000
16 | S 356th Street Culvert Replacement | 66 | 1400000 | 2020: 50000; 2023: 100000; 2024: 200000; 2025: 1050000
| Assumption: Potential for funding for the construction component of this project to improve fish passage |  |  | 2025: -500000
7 | Redondo Creek Culvert Replacement at 16th Ave S | 64 | 1100000 | 2021: 300000; 2023: 800000
| No outside funding assumed. |  |  | 2024: 0
43 | Outfall 256 Erosion Prevention Project | NA | 160000 | 2020: 160000
No outside funding assumed.
31 | South 359th Street Culvert Replacement | 60 | 890000 | 2024: 100000; 2025: 200000; 2026: 590000
No outside funding assumed.
36 | Hylebos Basin Land Acquisition | 52 | 2378000 | 1150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
| Project dependent on Forterra/SWC efforts |  |  | 2020: -1000000; 2021: significant grant funding included in assumed costs for this project i.e. $1M
37 | West Hylebos Educational Center Site Improvement | 46 | 1700000 | 2026: 1700000
No outside funding assumed. Project approval dependent on full CIP funding of 2021-2027 Rate.
41 | Citywide Water Quality Monitoring | 27 | 350000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
38 | North Fork West Hylebos Trail | 26 | 5200000 | 2023: 600000; 2024: 4600000
| Expected grant funding for 50% project costs. Project approval dependent on full CIP funding of 2021-2027 Rate. |  |  | 2023: -300000; 2024: -2300000
39 | West Hylebos Watershed Trail | 26 | 7800000 | 2024: 900000; 2025: 6900000
| Expected grant funding for 50% project costs. Project approval dependent on full CIP funding of 2021-2027 Rate. |  |  | 2024: -450000; 2025: -3450000
15 | Hidden Pond on Kim's Property | 25 | 60000 | 2022: 60000
No outside funding. Project approval dependent on full CIP funding of 2021-2027 Rate.
9 | 33rd Pl S Drainage Improvements | 16 | 340000 | 2021: Not funded. Continue to observe problem
No outside funding.
28 | 324th and 99 Drainage Improvements | 11 | 350000 | 2021: 150000; 2022: 200000
No outside funding.
32 | Upsize Pipes at SW Campus Dr. West of 9th Ave SW | 11 | 30000 | 2021: Not funded. Continue to observe problem
No outside funding.
Total for CIP Projects |  |  | 24838000 | 910000 | 1000000 | 1260000 | 2700000 | 3250000 | 4400000 | 2490000
Ongoing / Preservation Programs
25 | Catch Basin Repair | Mandatory | 525000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000
27 | Pipe Repair | Mandatory | 2052000 | 150000 | 317000 | 317000 | 317000 | 317000 | 317000 | 317000
35 | Annual CCTV Inspection and Assessment | Mandatory | 660000 | 160000 | 100000 | 100000 | 100000 | 100000 | 100000
42 | Annual Cost of SWM Support to City's Transportation Improvement Program | 36 | 2062000 | 50000 | 50000 | 343000 | 262000 | 50000 | 1157000 | 150000
1 | Neighborhood Drainage Improvements | Optional | 150000 |  | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
No outside funding. Project approval dependent on full CIP funding of 2021-2027 Rate.
Attachment 1
Note on B20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: "facility installation" deleted from name per discussion with City 7.24.19